## Feature Summary
Walrus Feature-Based Project Checklist
Checklist reorganized by App and Web/Admin features while preserving milestone, budget, and source traceability.
Total Checklist Items |  |  | Completed Items |  |  | Overall Progress |  |  | Total Budget
700
Area Summary | [5 empty] | Milestone Summary
Area | Items | Done | Progress | Primary Sheet |  | Milestone | Budget | Items | Done | Progress | Theme
Mobile App |  |  |  | App Checklist |  | M1 | 250 |  |  |  | Nền tảng và Kết nối lõi
Web/Admin + Backend |  |  |  | Web Backend Checklist |  | M2 | 280 |  |  |  | Hoàn thiện UI và Hệ thống quản trị
[6 empty] | M3 | 170 |  |  |  | Tính năng nâng cao và Bàn giao
Feature Checklist Summary | [6 empty] | How to Use
Area | Feature | Primary Milestone | Items | Done | Progress |  | 1. Work primarily in App Checklist and Web Backend Checklist.
Mobile App | Auth & Account | M1 |  |  |  |  | 2. Use Status, Owner, Due Date, and Notes to manage delivery.
Mobile App | Auth & Account | M2 |  |  |  |  | 3. Filter by Feature or Milestone depending on product or payment review.
Mobile App | Tuya Home Setup | M1 |  |  |  |  | 4. Milestone Map keeps the original source contract structure intact.
Mobile App | Device Pairing | M1
Mobile App | Core Device Control | M1
Mobile App | Smart Controls | M2
Mobile App | Mobile UI/UX | M2
Mobile App | Home Management | M2
Mobile App | Into the Cold | M3
Mobile App | Filter Reminder | M3
Mobile App | Push Notifications | M3
Mobile App | QA & Release | M3
Web/Admin + Backend | Backend Foundation | M2
Web/Admin + Backend | Device Mapping | M2
Web/Admin + Backend | Backend APIs | M2
Web/Admin + Backend | Admin Panel | M2
Web/Admin + Backend | Home Management Backend | M2
Web/Admin + Backend | Notifications Backend | M3
Web/Admin + Backend | Filter Reminder Backend | M3
Web/Admin + Backend | Operational Delivery | M3
Web/Admin + Backend | Tuya Operational Setup | M1

## App Checklist
App Feature Checklist
Feature-first checklist for all mobile app scope. Milestones are kept for delivery/payment tracking.
Use filters/dropdowns to track work by feature, milestone, owner, and status.
ID | Area | Feature | Milestone | Budget USD | Workstream | Checklist Item | Acceptance / Deliverable | Priority | Status | Owner | Due Date | Dependencies | Notes | Source
APP-001 | Mobile App | Auth & Account | M1 | $250 | Authentication | Email login flow | User can sign in with email and reach the app/home setup flow. | Cao | Chưa bắt đầu |  |  | Supabase/Tuya auth configuration |  | Overview #4; Milestone 1
APP-002 | Mobile App | Auth & Account | M1 | $250 | Authentication | Google Sign-In | Google login is wired into the app and creates/loads the same user profile. | Trung bình | Chưa bắt đầu |  |  | OAuth configuration |  | Overview #4
APP-003 | Mobile App | Auth & Account | M1 | $250 | Authentication | Apple Sign-In | Apple login works on iOS and maps to the same account/profile model. | Trung bình | Chưa bắt đầu |  |  | Apple developer configuration |  | Overview #4
APP-004 | Mobile App | Auth & Account | M2 | $280 | Profile | Account profile screen | User can view personal account information from the mobile app. | Cao | Chưa bắt đầu |  |  | Backend user profile table |  | Milestone 2
APP-005 | Mobile App | Auth & Account | M2 | $280 | Profile | Editable profile fields | Supported user profile fields can be updated and synced to backend/auth provider. | Cao | Chưa bắt đầu |  |  | Backend profile update API |  | Milestone 2
APP-006 | Mobile App | Tuya Home Setup | M1 | $250 | Tuya SDK | Home setup flow | User can create/select Tuya Home before device pairing. | Cao | Chưa bắt đầu |  |  | Tuya SDK initialized |  | Milestone 1
APP-007 | Mobile App | Tuya Home Setup | M1 | $250 | Tuya SDK | Owner permission validation | App surfaces clear error if the guest Tuya account is not Owner of the Home. | Cao | Chưa bắt đầu |  |  | Tuya account access |  | Technical notes
APP-008 | Mobile App | Tuya Home Setup | M1 | $250 | Tuya SDK | Data center compatibility guard | App configuration matches Tuya Cloud Project data center to prevent missing devices. | Cao | Chưa bắt đầu |  |  | Tuya Cloud Project region |  | Technical notes
APP-009 | Mobile App | Device Pairing | M1 | $250 | Pairing | WiFi pairing flow | User can enter/select WiFi network, enter password, and start pairing in-app. | Cao | Chưa bắt đầu |  |  | Location/WiFi permissions where applicable |  | Overview #4; Milestone 1
APP-010 | Mobile App | Device Pairing | M1 | $250 | Pairing | AP mode pairing flow | User can pair devices that require AP mode and receives clear mode instructions. | Cao | Chưa bắt đầu |  |  | Tuya SDK AP pairing support |  | Milestone 1
APP-011 | Mobile App | Device Pairing | M1 | $250 | Pairing | Bluetooth discovery/pairing | App can discover and connect supported Bluetooth devices through Tuya SDK. | Cao | Chưa bắt đầu |  |  | Bluetooth permission/configuration |  | Overview #3-4; Milestone 1
APP-012 | Mobile App | Device Pairing | M1 | $250 | Pairing UX | Pairing progress screen | Pairing enters a dedicated searching/progress screen with timeout and cancel behavior. | Cao | Chưa bắt đầu |  |  | Pairing start event |  | Milestone 1 deliverable
APP-013 | Mobile App | Device Pairing | M1 | $250 | Pairing | Successful bind to Home | Successfully paired device appears under the selected Tuya Home in the app. | Cao | Chưa bắt đầu |  |  | Tuya home setup complete |  | Milestone 1
APP-014 | Mobile App | Core Device Control | M1 | $250 | Dashboard | Current temperature display | Dashboard shows the real-time current water/device temperature from the device. | Cao | Chưa bắt đầu |  |  | Device paired and online |  | Overview #4; Milestone 1
APP-015 | Mobile App | Core Device Control | M1 | $250 | Dashboard | Target temperature control | User can change target temperature and command is sent to the real device. | Cao | Chưa bắt đầu |  |  | Device DP mapping |  | Milestone 1
APP-016 | Mobile App | Core Device Control | M1 | $250 | Device State | Command feedback and errors | App shows loading/success/failure states for temperature control commands. | Cao | Chưa bắt đầu |  |  | Tuya command callbacks |  | Milestone 1 deliverable
APP-017 | Mobile App | Smart Controls | M2 | $280 | Device Control | Light control | User can toggle/control device lighting from the custom UI. | Trung bình | Chưa bắt đầu |  |  | Device DP mapping |  | Overview #4
APP-018 | Mobile App | Smart Controls | M2 | $280 | Device Control | UV sterilization control | User can trigger/monitor UV sterilization controls from the app. | Trung bình | Chưa bắt đầu |  |  | Device DP mapping |  | Overview #4
APP-019 | Mobile App | Smart Controls | M2 | $280 | Device Control | Defrost control | User can trigger/monitor defrost behavior from the app. | Trung bình | Chưa bắt đầu |  |  | Device DP mapping |  | Overview #4
APP-020 | Mobile App | Mobile UI/UX | M2 | $280 | UI | Complete designed mobile screens | All required mobile screens match the design and core flows are connected. | Cao | Chưa bắt đầu |  |  | Design reference |  | Milestone 2
APP-021 | Mobile App | Mobile UI/UX | M2 | $280 | UX | Mobile responsiveness and usability | UI is optimized for common iOS/Android viewport sizes and touch interaction. | Cao | Chưa bắt đầu |  |  | Completed screens |  | Milestone 2
APP-022 | Mobile App | Home Management | M2 | $280 | Home | Room assignment | User/admin can assign devices to rooms within a Home. | Trung bình | Chưa bắt đầu |  |  | Backend persistence |  | Milestone 2
APP-023 | Mobile App | Home Management | M2 | $280 | Permissions | Device permission handling | Device access/permission behavior is represented correctly in the app. | Trung bình | Chưa bắt đầu |  |  | Home/room model |  | Milestone 2
APP-024 | Mobile App | Into the Cold | M3 | $170 | Timer | Into the Cold countdown | Countdown timer is available and works reliably during user sessions. | Trung bình | Chưa bắt đầu |  |  | App state handling |  | Overview #4; Milestone 3
APP-025 | Mobile App | Into the Cold | M3 | $170 | Activity | Daily activity summary | Daily activity summary is shown in app for the Into the Cold flow. | Trung bình | Chưa bắt đầu |  |  | Activity data storage |  | Milestone 3
APP-026 | Mobile App | Filter Reminder | M3 | $170 | Maintenance | Filter status display | App displays current filter reminder/status state to the user. | Trung bình | Chưa bắt đầu |  |  | Backend reminder state |  | Overview #4; Milestone 3
APP-027 | Mobile App | Filter Reminder | M3 | $170 | Maintenance | Filter reset action | User can reset filter reminder after replacement/maintenance. | Trung bình | Chưa bắt đầu |  |  | Backend reset persistence |  | Milestone 3
APP-028 | Mobile App | Filter Reminder | M3 | $170 | Maintenance | Buy-filter link | App includes a link/action to buy a new filter. | Thấp | Chưa bắt đầu |  |  | Final purchase URL |  | Milestone 3
APP-029 | Mobile App | Push Notifications | M3 | $170 | Notifications | Notification permission and token flow | App asks permission and registers FCM/APNs token for notifications. | Cao | Chưa bắt đầu |  |  | Firebase configuration |  | Overview #3; Milestone 3
APP-030 | Mobile App | Push Notifications | M3 | $170 | Notifications | Cleanup/status alerts in app | Cleanup reminders and status alerts are received/displayed correctly. | Cao | Chưa bắt đầu |  |  | Backend notification rules |  | Milestone 3
APP-031 | Mobile App | QA & Release | M3 | $170 | Testing | Real-device end-to-end test | A full real-device flow passes: login, home setup, pair, control, notification. | Cao | Chưa bắt đầu |  |  | Device access |  | Milestone 3
APP-032 | Mobile App | QA & Release | M3 | $170 | Delivery | Mobile release build | Final app build is prepared for handoff/deployment. | Cao | Chưa bắt đầu |  |  | Testing complete |  | Milestone 3

## Web Backend Checklist
Web/Admin + Backend Feature Checklist
Feature-first checklist for admin web, backend, notification infrastructure, and operational handoff.
Use filters/dropdowns to track work by feature, milestone, owner, and status.
ID | Area | Feature | Milestone | Budget USD | Workstream | Checklist Item | Acceptance / Deliverable | Priority | Status | Owner | Due Date | Dependencies | Notes | Source
WEB-001 | Web/Admin + Backend | Backend Foundation | M2 | $280 | Supabase | Supabase project and schema | Backend stores user profiles and core app records in Supabase. | Cao | Chưa bắt đầu |  |  | Project credentials |  | Overview #3; Milestone 2
WEB-002 | Web/Admin + Backend | Backend Foundation | M2 | $280 | User Profile | User profile persistence | Profile data created/updated from auth and app flows is persisted consistently. | Cao | Chưa bắt đầu |  |  | Auth integration |  | Milestone 2
WEB-003 | Web/Admin + Backend | Device Mapping | M2 | $280 | Data Model | Device mapping storage | Backend stores mapping between app user, Tuya Home, and linked devices. | Cao | Chưa bắt đầu |  |  | Successful Tuya pairing |  | Milestone 2
WEB-004 | Web/Admin + Backend | Device Mapping | M2 | $280 | Sync | Device mapping sync API | App can read/write device mapping through stable backend/Vercel APIs. | Cao | Chưa bắt đầu |  |  | Vercel API setup |  | Milestone 2
WEB-005 | Web/Admin + Backend | Backend APIs | M2 | $280 | Vercel | Vercel API deployment | Backend APIs are deployed on Vercel and reachable by the mobile app. | Cao | Chưa bắt đầu |  |  | Environment variables |  | Overview #3; Milestone 2
WEB-006 | Web/Admin + Backend | Backend APIs | M2 | $280 | Sync | Stable app/backend data sync | User profile, device mapping, and usage data sync without data loss in normal flows. | Cao | Chưa bắt đầu |  |  | Supabase schema complete |  | Milestone 2 deliverable
WEB-007 | Web/Admin + Backend | Admin Panel | M2 | $280 | Admin UI | Admin access control | Admin panel is protected so only authorized admins can access operational data. | Cao | Chưa bắt đầu |  |  | Admin identity/role model |  | Overview #4; Milestone 2
WEB-008 | Web/Admin + Backend | Admin Panel | M2 | $280 | Admin UI | User list view | Admin can view the user list with relevant account/profile fields. | Cao | Chưa bắt đầu |  |  | User profile table |  | Milestone 2
WEB-009 | Web/Admin + Backend | Admin Panel | M2 | $280 | Admin UI | Linked device view | Admin can view linked devices per user/home. | Cao | Chưa bắt đầu |  |  | Device mapping table |  | Overview #4; Milestone 2
WEB-010 | Web/Admin + Backend | Admin Panel | M2 | $280 | Admin UI | Device status monitoring | Admin can monitor device online/status information where available. | Trung bình | Chưa bắt đầu |  |  | Tuya status data availability |  | Milestone 2
WEB-011 | Web/Admin + Backend | Admin Panel | M2 | $280 | Admin UI | Usage data view | Admin can view basic usage data required for operations. | Trung bình | Chưa bắt đầu |  |  | Usage events stored |  | Overview #4; Milestone 2
WEB-012 | Web/Admin + Backend | Home Management Backend | M2 | $280 | Data Model | Rooms and device permissions persistence | Room assignment and permission-related records are stored and retrievable. | Trung bình | Chưa bắt đầu |  |  | Home management UI/API |  | Milestone 2
WEB-013 | Web/Admin + Backend | Notifications Backend | M3 | $170 | FCM | Firebase/FCM backend setup | Backend can send push notifications through Firebase Cloud Messaging. | Cao | Chưa bắt đầu |  |  | Firebase project credentials |  | Overview #3; Milestone 3
WEB-014 | Web/Admin + Backend | Notifications Backend | M3 | $170 | Rules | Cleanup and status alert rules | Notification rules cover cleanup reminders and device/status alerts. | Trung bình | Chưa bắt đầu |  |  | Token registration |  | Milestone 3
WEB-015 | Web/Admin + Backend | Filter Reminder Backend | M3 | $170 | Maintenance | Filter reminder backend state | Backend stores filter reminder state and supports reset updates. | Trung bình | Chưa bắt đầu |  |  | User/device mapping |  | Milestone 3
WEB-016 | Web/Admin + Backend | Operational Delivery | M3 | $170 | Testing | Backend/admin test pass | Backend APIs and admin panel pass core regression testing. | Cao | Chưa bắt đầu |  |  | Feature completion |  | Milestone 3
WEB-017 | Web/Admin + Backend | Operational Delivery | M3 | $170 | Deployment | Production deployment checklist | Vercel/Supabase/Firebase configuration is documented and deployment-ready. | Cao | Chưa bắt đầu |  |  | Environment review |  | Milestone 3
WEB-018 | Web/Admin + Backend | Operational Delivery | M3 | $170 | Handoff | Source code and handoff docs | Source code, setup notes, and required credentials/configuration list are handed over. | Cao | Chưa bắt đầu |  |  | Final QA complete |  | Milestone 3
WEB-019 | Web/Admin + Backend | Tuya Operational Setup | M1 | $250 | Tuya Cloud | Tuya Cloud Project region check | Tuya Cloud Project and Tuya account use the same Data Center. | Cao | Chưa bắt đầu |  |  | Tuya account/cloud access |  | Technical notes
WEB-020 | Web/Admin + Backend | Tuya Operational Setup | M1 | $250 | Tuya Home | Guest account owner check | Provided guest account is Owner of Tuya Home before SDK linking. | Cao | Chưa bắt đầu |  |  | Tuya Home access |  | Technical notes

## Milestone Map
Original Milestone Map
Original milestone/budget structure from the source document, kept for acceptance and payment review.
Milestone | Budget USD | Original Theme | Source Scope | Source Deliverable | App Feature Link | Web/Backend Feature Link | Technical Notes
M1 | 250 | Nền tảng và Kết nối lõi (Foundation & Core Control) | React Native CLI + Tuya SDK; login/home setup; in-app pairing WiFi/Bluetooth; basic temperature dashboard/control. | Build app can pair with real device and perform basic temperature commands. | Auth & Account; Tuya Home Setup; Device Pairing; Core Device Control | Tuya Operational Setup | Tuya account and Cloud Project must use same Data Center; guest account must be Tuya Home Owner.
M2 | 280 | Hoàn thiện UI và Hệ thống quản trị (UI Completion & Backend) | Complete mobile UI; Supabase/Vercel backend; user profile; device mapping; home management; admin panel. | Complete UI, stable backend sync, and admin page for operational management. | Mobile UI/UX; Smart Controls; Home Management; Account Profile | Backend Foundation; Device Mapping; Backend APIs; Admin Panel; Home Management Backend | Backend on Supabase/Vercel with stable data sync.
M3 | 170 | Tính năng nâng cao và Bàn giao (Advanced Features & Delivery) | Into the Cold; push notifications; filter reminders; testing; performance; deployment and source handoff. | App is complete for end users with handoff documentation. | Into the Cold; Push Notifications; Filter Reminder; QA & Release | Notifications Backend; Filter Reminder Backend; Operational Delivery | FCM notifications; testing, performance, deployment, and source handoff.

## Source Notes
Source Notes & Assumptions
Traceability for the checklist rows and how feature grouping was interpreted.
Source | Path | Used For | Key Extracted Scope | Assumption / Interpretation | Review Note
Project Overview | docs/TÀI-LIỆU-1-TỔNG-QUAN-DỰ-ÁN-(PROJECT-OVERVIEW).txt | Feature taxonomy | Mobile app, Tuya SDK, Supabase/Vercel, FCM, pairing, smart control, account, Into the Cold, filter reminder, home management, admin panel. | Rows were grouped by product feature area first, not payment milestone. | Keep as baseline product scope.
Milestone Document | docs/TÀI-LIỆU-2-CHI-TIẾT-CÁC-CỘT-MỐC-(MILESTONE-DOCUMENT).txt | Milestone/budget/acceptance mapping | M1 $250, M2 $280, M3 $170 with deliverables and technical Tuya notes. | Milestone and budget columns remain as metadata for acceptance/payment review. | Use Milestone Map for contract-level review.
Feature grouping | Derived from both docs | Workbook structure | App features are separated from Web/Admin + Backend features. | Backend items are grouped with Web/Admin because the admin panel and operational APIs are delivered as the web/backend layer. | Adjust Area labels if the team wants a separate Backend sheet.